## Sheet1
Bug_Id | Bug_Description | Display | Image_reference | QC Status | Dev Status
1 | Need to show the the Valid Password Criteria when create the user. | User | SS_1 | Open | Done
2 | Account Expiry should be of future date. | User | SS_2 | Open | Done
3 | Expired Accounts should not be allowed to login | Login |  | Open | Done
4 | Showing ''Something went wrong" when check the user profile. | Dashboard | SS_3 | Open | Done
5 | Showing ''Something went wrong" when change the password. | Dashboard | SS_4 | Open | Done
6 | Unable to open System Setting. Loader is showing continue. | Dashboard | SS_5 | Open | Done
7 | Need to show "manufacturer" instead of "manufacture" | Confoguration->Manufacturer | SS_6 | Open | Done
8 | TransactionType Graph should be meaningfull . | Dashboard | SS_7 | Open | last 24 hour vehcile count based on trans type
9 | Need to show validation Message when create the new Manufacturer. | Confoguration->Manufacturer | SS_8 | Open | Done
10 | Mention the Criteria message for LoginId and Login Pasword when add the manufacturer. | Confoguration->System Integrator | SS_9 | Open | Done
11 | Fare Changes should not be allowed for current date. | Confoguration->Fare | SS_11 | Open | Working Fine
12 | Journey Name should be available | Confoguration->Fare | SS_10 | Open | Done
13 | Unable to update the Equipments | Confoguration->Equipment | SS_12 | Open | Working Fine
14 | Unable to update the Lanes | Confoguration->Lane | SS_13 | Open | Done
15 | Float Process Is wrong. 1- New float shoud be allowed for only current and future shift. 2- Mid Float should be allowed only for current shift. 3- End Float should only allowed for previous shift. | Float Management-> Float Process | SS_14 | Open | Done
16 | Receipt Functionality is pending | Float Management-> Float Process |  | Open | Done
17 | Unable to g on Dashboard page from other page. |  | SS_15 | Open | Done
18 | Need to show Eye icon on login page. | Login Page | SS_16 | Open | Done
19 | Display Plaza name on Screen |  |  | Open | Done
20 | Validation must me meaningfull(Reason for invalid when enter the loginid and password) | User |  | Open | Done
21 | PhoneNumber is showing instead of Password. And password must be hide | Confoguration->System Integrator |  | Open | Eye icon implementd
22 | Everytime asking password when uppdate | Confoguration->System Integrator |  | Open | Working Fine
23 | Fare should not be saved for current date. Should only allowed for future date. |  |  | Open | Working Fine
24 | Fare is not available to update for created plaza |  |  | Open | Working Fine
25 | Unable to redirect on Dashboard page. After any user login |  |  | Open | Done
26 | Dashbord data is wrong as no transactrion in table while dashboard is showing lane transaction on graph. |  |  | Open | Done
27 | Role and permission functionality not working properly.For reference Auditor user is created. |  |  | Open | Done
28 | Able to create the users for multiple plaza which is wronhg. Plazawise user functionality wrong | User |  |  | Done
29 | Cash float should not be allowed for backdate. Able to crETE ENTRY FOR BACKDATE AND INVALID DATE IS SHOWING ON ui FOR THAT ENTRY. |  |  |  | Done
30 | Difference amount is wrong in audit section. Transaction is created for reference.
31 | Need to provide some provision to cancel the transactions. |  |  |  | In progress
32 | Plate number is not available in audit section. Need to provide. |  |  |  | Done
33 | Transaction Datetime and Ui date time is wrong.
34 | Reaudit functionality is required.
35 | Transaction amount and difference amount is wrong
36 | Cancel exempt is not available.
37 | Added remark is not available which was entered during review the transaction |  |  |  | Done
38 | Shift clearence- not complate. Require complete shift details to show.
39 | Duplicate entries on clearance page.
40 | Wrong msg when update the user password. Showing "Password not changed" | Change Password |  |  | Done