## Bug Report
| Project: |  | Assign To
| Module Name: | Toll 360 | Tested By | Pankaj Sharma
| Operating System: | Window 10
Version:
Defect Id | Description | Test case Id | Bug Type | Reproducible Steps | Status | Severity | Priority | Test Cycle | Snapshot | Fixed by | Developer comment | QC Comment
1 | Clicking on dashboard shows that "Dashboard Works!". |  | Suggestion | Click on dashboard. | New | Trivial | Low | Test Cycle 2 |  |  | Dashbard is pending
2 | Unable to create client from client configuration. Save button or icon not reflecting. |  | Validation | Click on client configuration. | Fixed | Major | High | Test Cycle1 |  |  |  | Fixed
3 | Unable to create plaza as client can't be created. |  | Validation | Click on plaza configuration. | Fixed | Major | High | Test Cycle1 |  |  |  | Fixed
4 | What is the use of FTP path, login id, password, data send/receive API? |  | Suggestion | Creation of plaza in plaza configuration. | New | Trivial | Low | Test Cycle1 |  |  | FTP will remove from UI and API path help to transfering the data
5 | Client id in client configuration grid is not in numeric series. |  | GUI | Click on client configuration. | New | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid
6 | Plaza id in plaza configuration grid is not in numeric series. |  | GUI | Click on plaza configuration. | New | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid
7 | Lane id in lane configuration grid is not in numeries series. |  | GUI | Click on lane configuration. | New | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid
8 | In hardware configuration, while creating new hardware, dropdown filter of plaza is reflecting only one plaza name for selection. |  | Validation | Click on hadrware configuration -> Click on + button. | New | Major | High | Test Cycle1 |  |  | Plaza will display according to client
9 | In hardware configuration, first row in a grid is not reflecting completely. |  | GUI | Click on hardware configuration. | New | Medium | Medium | Test Cycle1 |  |  | user Screen resolution 1368*768
10 | Hardware ID in hardware configuration grid is not in numeric series. |  | GUI | Click on hardware configuration. | New | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid
11 | The names for Vehicle Class is not matching. While adding a new vehicle, vehicle class mapping screen was shown. |  | GUI | Click on vehicle class -> Click on + button. | New | Trivial | Low | Test Cycle1
12 | In vehicle class configuration, first row in a grid is not reflecting completely names of column. |  | GUI | Click on vehicle class. | New | Medium | Medium | Test Cycle1 |  |  | user Screen resolution 1368*768
13 | Unable to create a vehicle class. AVC class and IHMCL class not configured. |  | Validation | Click on vehicle class -> Click on + button. | New | Major | High | Test Cycle1 |  |  | Import the ACV class
14 | Fare mapping is not opening since there was not vehicle class configured. |  | Functional | Click on fare mapping. | New | Major | High | Test Cycle1
15 | Role id in role configuration is not in numeric series. |  | GUI | Click on role configuration. | New | Trivial | Low | Test Cycle1 |  |  | Last created and modified data come first poition of grid
16 | In user configuration, only one plaza was shown in dropdown filter. |  | Validation | Click on user configuration. | New | Major | High | Test Cycle1 |  |  | Plaza will display according to client
17 | Clicking on reports, error 404 is reflecting. |  | Functional | Click on reports. | New | Major | High | Test Cycle1 |  |  | Reporting is pending
Cosmetic
Test Cycle1
High | Blocker | New |  | Functional | Test Cycle 2
Medium | Major | Open |  | Validation | Test Cycle 3
Low | Medium | Fixed |  | Truncation | Test Cycle 4
| Trivial | Reopen |  | Cosmetic | Test Cycle 5
|  | Verified |  | GUI | Test Cycle 6
|  | Closed |  | Typo | Test Cycle 7
|  | Differed |  | Suggestion | Test Cycle 8
|  | Not Reproduced |  | Requirement | Test Cycle 9
|  | New(Re QA) |  |  | Test Cycle 10
Pankaj Sharma