## Bug Report
| Project: |  | Assign To
| Module Name: | Toll 360, Cashup, Audit, Central Server | Tested By | Madhav Singh
| Operating System: | Window 10
Version:
Defect Id | Description | Test case Id | Bug Type | Reproducible Steps | Status | Severity | Priority | Test Cycle | Snapshot | Fixed by | Developer comment | QC Comment | Dated | Testesd By
1 | Record window should be closed, before user saved the records. |  | GUI | Demo Popup Window | New | Medium | Medium | Test Cycle1 |  |  | Not a bug this is demo app will remove after lane module ready |  | 2021-05-12 | Madhav Singh
2 | User search the record date of 8th may but message is coming "No data Found". |  | GUI | No data Found msg | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-12 | Madhav Singh
3 | All column name fields should be proper displayed, and date filter search records should be proper place. |  | GUI | Filter search | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-12 | Madhav Singh
4 | User is able to clicking on cross sign icon only filtered records should be reseted. Click on cross icon grid number of rows increases. |  | GUI | Filter search | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-12 | Madhav Singh
5 | Before Review records saved successfully but popup window still there, wondow should be removed. |  | Functional | Review page window | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-12 | Madhav Singh
6 | User is able to click on Save button message is showing "Mid clearance not allowed for future shift." (Cashup) |  | GUI | Msg Issue | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-12 | Madhav Singh
7 | User alloted the cash receipt in future date easily. (Cashup) |  | Functional | Future date issue | New | Medium | Medium | Test Cycle1 |  |  | cash allotment can be done for future. Because its need berofe shift start |  | 2021-05-12 | Madhav Singh
8 | Records already displayed in grid fields, user give the print message is showing 'No Data Found'. |  | GUI | Msg Issue | New | Medium | Medium | Test Cycle1 |  |  | SELECT on allotment option |  | 2021-05-12 | Madhav Singh
9 | In Review transaction page, search records page header name will be "Lane Transactions Details" Only. |  | GUI | Page header name | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-13 | Madhav Singh
10 | Inhardware configuration, client configuration table modifiedby and Createdby should be displayed. |  | Functional | modify and created | New | Medium | Medium | Test Cycle1 |  |  | You can Use your esxting table for harwdare (harwdareTest ) Please discuss with hasir sir on this |  | 2021-05-14 | Madhav Singh
11 | Fare is not updated in backend, before user entered the fare amound front end based. |  | Functional | Fare | New | Medium | Medium | Test Cycle1 |  |  | Alredy demonstrate yesterday meeting (Done) |  | 2021-05-14 | Madhav Singh
12 | Unique exempt id should be displayed, client id can't be null. |  | Functional | Exemption type | New | Medium | Medium | Test Cycle1 |  |  | client id not required because it's used for each client and each plaza |  | 2021-05-14 | Madhav Singh
13 | User is able to select central server and create the user, user is not showing plaza server details. |  | Functional | data issue | New | Major | High | Test Cycle1 |  |  | create central server user no need to sink to plaza |  | 2021-05-17 | Madhav Singh
14 | Naming convention issue in create user form (central server) |  | GUI | naming | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-17 | Madhav Singh
15 | Naming convention issue (Violation) in Transaction Type Details page.(central Server) |  | GUI | Naming convention issue | New | Trivial | Low | Test Cycle1 |  |  | Done |  | 2021-05-08 | Madhav Singh
16 | In Client configuration page mobile number should be 10 digit only. (central Server) |  | GUI | Mobile number issue | New | Medium | Medium | Test Cycle1 |  |  | Done | Fixed | 2021-05-08 | Madhav Singh
17 | User is not able to click on status check box field popup message should be proper displayed and close.(Client configuration page) |  | GUI | Message issue | New | Major | High | Test Cycle1 |  |  | need discussion | The issue has already been discussed for cross error sign. Need a resolution. | 2021-05-08 | Madhav Singh
18 | Special character should not be allowed in Name, Address, Mobile Number, Email (except@) (Client configuration page). |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Done:We can ignore in name and mobile number | Done | 2021-05-08 | Madhav Singh
19 | In Exempt configuration page filter search functionality are not working. |  | Functional | Search Issue | New | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
20 | Creating or Editing fields Special character should not be allowed in Exemption Name Field. |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
21 | Creating or Editing fields Special character should not be allowed in Plaza Configuration Page. |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
22 | Page should be maximized or minimized over clicking mouse. The zoom-in and zoom-out option should be there with a single button. |  | GUI | Max or min by click mouse | New | Medium | Medium | Test Cycle1 |  |  | Need discussion | The page zoom-in and zoom-out button is not functional. | 2021-05-08 | Madhav Singh
23 | active or Inactive record should be update in plaza mapping page. |  | Functional | Active/Inactive | New | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
24 | Creating or Editing records Special character should not be allowed in Lane Configuration Page (Lane IP). |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Working Fine, need to press tab or click the save icon to check the validaton (Not a bug) | Fixed | 2021-05-08 | Madhav Singh
25 | Creating or Editing records Special character should not be allowed in Vehicle class Configuration Page (Vehicle Weight). |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Working Fine (Not a bug) | Not Fixed | 2021-05-08 | Madhav Singh
26 | In fare configuration Page Refresh button is not working.(Before user search the records). |  | Functional | Refresh button issue | New | Major | High | Test Cycle1 |  |  | Reload button is depend on effective date selection, for example select any date and need to click on reload button its will display data depend selected date. today is 9th of may and you choose 10th may and clieck on reload then it will show data for 9th may and date will be auto set for 9th may. | In the search filter, whatever name was entered and need to reset a searched filter, the refresh button is not functional. | 2021-05-08 | Madhav Singh
27 | Column name 'Connection Address' should be proper visible in hardware configuration page. |  | GUI | visibility issue | New | Medium | Medium | Test Cycle1 |  |  | already shared: used Screen resolution 1368*768 | Fixed | 2021-05-10 | Madhav Singh
28 | Reset Password save button should be required. |  | Functional | Button | New | Major | High | Test Cycle1 |  |  | Done : Reset password not used for super account, You can create new user and test again |  | 2021-05-10 | Madhav Singh
29 | Logout popup window cross sign should be removed. |  | GUI | Cross icon | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-10 | Madhav Singh
30 | User click on save button effective date should not be refreshed,data should be saved only. (Fare Configuration) |  | Functional | Save button | New | Major | High | Test Cycle1 |  |  | Need discussion |  | 2021-05-10 | Madhav Singh
31 | Error message should be proper displayed, the case of before user enter the same role name after clicking on save button. (User role page). |  | GUI | Message issue | New | Medium | Medium | Test Cycle1 |  |  | Done | The proper message should be displayed, whether an entry is saved or not. | 2021-05-10 | Madhav Singh
32 | User is able to logged in the webpage at a time user clicking on url refresh button, all page should be closed and session logout automatically.(show only login page) |  | Functional | page issue | New | Major | High | Test Cycle1 |  |  | Pending |  | 2021-05-10 | Madhav Singh
Cosmetic
Test Cycle1
High | Blocker | New |  | Functional | Test Cycle 2
Medium | Major | Open |  | Validation | Test Cycle 3
Low | Medium | Fixed |  | Truncation | Test Cycle 4
| Trivial | Reopen |  | Cosmetic | Test Cycle 5
|  | Verified |  | GUI | Test Cycle 6
|  | Closed |  | Typo | Test Cycle 7
|  | Differed |  | Suggestion | Test Cycle 8
|  | Not Reproduced |  | Requirement | Test Cycle 9
|  | New(Re QA) |  |  | Test Cycle 10
Pankaj Sharma
Madhav Singh

## Developer Evidence
Note : Each validation run after tab press or click on save icon
Point 25
|  | Point 31 |  | Point 31
Bug Number 37

## Evidence
Defect Id | Snapshot
1
2
3
4
5
6
7
8
9
10
11
12
13
14