## Bug Report
| Project: |  | Assign To
| Module Name: | Toll 360, Cashup | Tested By | Pankaj Sharma
| Operating System: | Window 10
Version:
Defect Id | Description | Test case Id | Bug Type | Reproducible Steps | Status | Severity | Priority | Test Cycle | Snapshot | Fixed by | Developer comment | QC Comment
1 | Spell check - Slot Id is mentioned as Sloat Id. |  | Typo | See for the column 2. | New | Major | High | Test Cycle1 |  |  | Done
2 | While creating a new entry, in shift dropdown filter, rather than timmings , shift 1, shift 2 and shift 3 needs to be displayed. |  | Validation | Click on create new entry. | New | Medium | Medium | Test Cycle1 |  |  | Done
3 | Click on Print button, the printing of receipt required receipt number. On GUI no receipt number is displayed. |  | Functional | Click on Print button. | New | Major | High | Test Cycle1
4 | Shift end declaration is missing in the module. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Done
5 | Receipt number is only mentioned in the generated receipt, but also required to be displayed in the grid. |  | GUI |  | New | Medium | High | Test Cycle1 |  |  | Allotment Receipt Number displayed
6 | Shift timming is required to be renamed as Shift Id in the column. |  | GUI |  | New | Medium | Medium | Test Cycle1 |  |  | Done
7 | Mid shift declare could be declared for future date. The mid shift should be allowed only for current running shift only. |  | Functional | Click on mid shift and declare amount for future date. | New | Major | High | Test Cycle1 |  |  | Done
Cosmetic
Test Cycle1
High | Blocker | New |  | Functional | Test Cycle 2
Medium | Major | Open |  | Validation | Test Cycle 3
Low | Medium | Fixed |  | Truncation | Test Cycle 4
| Trivial | Reopen |  | Cosmetic | Test Cycle 5
|  | Verified |  | GUI | Test Cycle 6
|  | Closed |  | Typo | Test Cycle 7
|  | Differed |  | Suggestion | Test Cycle 8
|  | Not Reproduced |  | Requirement | Test Cycle 9
|  | New(Re QA) |  |  | Test Cycle 10
Pankaj Sharma