## Bug Report
| Project: |  | Assign To
| Module Name: | Toll 360, Cashup, Audit | Tested By | Pankaj Sharma
| Operating System: | Window 10
Version:
Defect Id | Description | Test case Id | Bug Type | Reproducible Steps | Status | Severity | Priority | Test Cycle | Snapshot | Fixed by | Developer comment | QC Comment | Dated | Testesd By
1 | Spell check - Slot Id is mentioned as Sloat Id. |  | Typo | See for the column 2. | Fixed | Major | High | Test Cycle1 |  |  | Done | Fixed | 2021-05-05
2 | While creating a new entry, in shift dropdown filter, rather than timmings , shift 1, shift 2 and shift 3 needs to be displayed. |  | Validation | Click on create new entry. | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Fixed | 2021-05-05
3 | Click on Print button, the printing of receipt required receipt number. On GUI no receipt number is displayed. |  | Functional | Click on Print button. | Fixed | Major | High | Test Cycle1 |  |  |  | Fixed | 2021-05-05
4 | Shift end declaration is missing in the module. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Fixed | 2021-05-05
5 | Receipt number is only mentioned in the generated receipt, but also required to be displayed in the grid. |  | GUI |  | Fixed | Medium | High | Test Cycle1 |  |  | Allotment Receipt Number displayed | Fixed | 2021-05-05
6 | Shift timming is required to be renamed as Shift Id in the column. |  | GUI |  | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Fixed | 2021-05-05
7 | Mid shift declare could be declared for future date. The mid shift should be allowed only for current running shift only. |  | Functional | Click on mid shift and declare amount for future date. | Fixed | Major | High | Test Cycle1 |  |  | Done | Fixed | 2021-05-05
8 | Reset button is not available to clear entries from a grid. |  | Functional | See for the review transaction page. | New | Major | High | Test Cycle1 |  |  | Done |  | 2021-05-07
9 | Filter data details are not hiding from the form. |  | Validation | Check for the spelling of Proof in transaction details pop-up. | New | Major | High | Test Cycle1 |  |  | Done:its will show/hide on click of filter icon |  | 2021-05-07
10 | Spell check: Proof spelling is displaying as Proff in transaction details. |  | Typo | Click on filter data button. | New | Major | High | Test Cycle1 |  |  | Done |  | 2021-05-07
11 | Only last transaction details is displaying in the transaction when filtered. Unable to switch to another transaction in the same pop-up untill reviewed. |  | Functional | See for the transaction details pop-up. | New | Major | High | Test Cycle1 |  |  | Need discussion |  | 2021-05-07
12 | The image and video displaying are same for every transaction. Even video is not buffering. |  | Functional | See for the transaction details pop-up. | New | Major | High | Test Cycle1 |  |  | its dummy data |  | 2021-05-07
13 | Separate pop-up is required for the filter data, which will be very much clear in visual and functional process. |  | Validation | Click on filter data button. | New | Medium | Medium | Test Cycle1 |  |  | Need discussion |  | 2021-05-07
14 | The page for review required filter is not refreshing. The transaction is displayed in the grid after review. |  | Functional | Select review required filter from filter data. | New | Major | High | Test Cycle1 |  |  | Need discussion |  | 2021-05-07
15 | While clicking on the clearance button, mid clearance is only possible. Even allotment amount doesn't changes as per entered denominations. |  | Functional | Click on clearance button, enter denominations and click on save button. | New | Major | High | Test Cycle1 |  |  | Allotment amount is that fixed its will never change.each clearence willstore in sperate coloum that is deposit. Final stalement will done in shift close. |  | 2021-05-07
16 | For current date and shift, mid shift declare is not allowed. Message displayed as "Mid shift declare is not allowed for future shift." |  | Functional | Declare mid shift. | New | Major | High | Test Cycle1 |  |  | Need discussion |  | 2021-05-07
17 | After clearance of a particular user and shift, the shift status is showing as pending in the grid. |  | Functional | See for the details in a grid after clearance. | New | Major | High | Test Cycle1 |  |  | Shift showing pending untill its is not closed and when its closed it will remove from the grid |  | 2021-05-07
18 | While closing a sift, message appear as "Lane is not close this shift". The statement is contradictory. |  | Functional | Close a shift from shift details. | New | Major | High | Test Cycle1 |  |  | this meaasge is used to validate the lane trans are synced or not |  | 2021-05-08 | Madhav Singh
19 | Click on review transaction, and the details of last processed transaction automatically displayed without selecting filter data. |  | Functional | Click on review transaction. | New | Major | High | Test Cycle1 |  |  | Need discussion |  | 2021-05-08 | Madhav Singh
20 | Lane transaction details-1 or 2 or 3 is displayed in a pop-up, which is not required. Clicking on a transaction should display details of that particular transaction. |  | Suggestion | Click on transaction displaying in a grid. | New | Major | High | Test Cycle1 |  |  |  |  | 2021-05-08 | Madhav Singh
21 | Naming convention issue (Violation) in Transaction Type Details page.(central Server) |  | GUI | Naming convention issue | New | Trivial | Low | Test Cycle1 |  |  |  |  | 2021-05-08 | Madhav Singh
22 | In Client configuration page mobile number should be 10 digit only. (central Server) |  | GUI | Mobile number issue | New | Medium | Medium | Test Cycle1 |  |  | In our country mobile number length is increased up to 11 digit (Not a bug) | Not Fixed | 2021-05-08 | Madhav Singh
23 | User is not able to click on status check box field popup message should be proper displayed and close.(Client configuration page) |  | GUI | Message issue | New | Major | High | Test Cycle1 |  |  | need discussion |  | 2021-05-08 | Madhav Singh
24 | Special character should not be allowed in Name, Address, Mobile Number, Email (except@) (Client configuration page). |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Done:We can ignore in name and mobile number |  | 2021-05-08 | Madhav Singh
25 | In Exempt configuration page filter search functionality are not working. |  | Functional | Search Issue | New | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
26 | Creating or Editing fields Special character should not be allowed in Exemption Name Field. |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
27 | Creating or Editing fields Special character should not be allowed in Plaza Configuration Page. |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
28 | Page should be maximized or minimized over clicking mouse. |  | GUI | Max or min by click mouse | New | Medium | Medium | Test Cycle1 |  |  | Need discussion |  | 2021-05-08 | Madhav Singh
29 | active or Inactive record should be update in plaza mapping page. |  | Functional | Active/Inactive | New | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-08 | Madhav Singh
30 | Creating or Editing records Special character should not be allowed in Lane Configuration Page (Lane IP). |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Working Fine, need to press tab or click the save icon to check the validaton (Not a bug) | Not Fixed | 2021-05-08 | Madhav Singh
31 | Creating or Editing records Special character should not be allowed in Vehicle class Configuration Page (Vehicle Weight). |  | GUI | Special charcter issue | New | Medium | Medium | Test Cycle1 |  |  | Working Fine (Not a bug) | Not Fixed | 2021-05-08 | Madhav Singh
32 | In fare configuration Page Refresh button is not working.(Before user search the records). |  | Functional | Refresh button issue | New | Major | High | Test Cycle1 |  |  | Reload button is depend on effective date selection, for example select any date and need to click on reload button its will display data depend selected date. today is 9th of may and you choose 10th may and clieck on reload then it will show data for 9th may and date will be auto set for 9th may. | Not Fixed | 2021-05-08 | Madhav Singh
33 | Column name 'Connection Address' should be proper visible in hardware configuration page. |  | GUI | visibility issue | New | Medium | Medium | Test Cycle1 |  |  | already shared: used Screen resolution 1368*768 |  | 2021-05-10 | Madhav Singh
34 | Reset Password save button should be required. |  | Functional | Button | New | Major | High | Test Cycle1 |  |  | Done : Reset password not used for super account, You can create new user and test again |  | 2021-05-10 | Madhav Singh
35 | Logout popup window cross sign should be removed. |  | GUI | Cross icon | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-10 | Madhav Singh
36 | User click on save button effective date should not be refreshed,data should be saved only. (Fare Configuration) |  | Functional | Save button | New | Major | High | Test Cycle1 |  |  | Need discussion |  | 2021-05-10 | Madhav Singh
37 | Error message should be proper displayed, the case of before user enter the same role name after clicking on save button. (User role page). |  | GUI | Message issue | New | Medium | Medium | Test Cycle1 |  |  | Done |  | 2021-05-10 | Madhav Singh
38 | User is able to logged in the webpage at a time user clicking on url refresh button, all page should be closed and session logout automatically.(show only login page) |  | Functional | page issue | New | Major | High | Test Cycle1 |  |  | Pending |  | 2021-05-10 | Madhav Singh
Cosmetic
Test Cycle1
High | Blocker | New |  | Functional | Test Cycle 2
Medium | Major | Open |  | Validation | Test Cycle 3
Low | Medium | Fixed |  | Truncation | Test Cycle 4
| Trivial | Reopen |  | Cosmetic | Test Cycle 5
|  | Verified |  | GUI | Test Cycle 6
|  | Closed |  | Typo | Test Cycle 7
|  | Differed |  | Suggestion | Test Cycle 8
|  | Not Reproduced |  | Requirement | Test Cycle 9
|  | New(Re QA) |  |  | Test Cycle 10
Pankaj Sharma
Madhav Singh

## Developer Evidence
Note : Each validation run after tab press or click on save icon
| Bug Number 30 |  |  | Bug Number 22
|  | Bug Number 31 |  | Bug Number 33
|  | Bug Number 32 & 36 | Bug Number 32 & 36 |  |  | Bug Number 32 & 36
Bug Number 32 & 36

## Evidence
Defect Id | Snapshot_Name
30 | Snap_laneIP
31 | Snap_vehicleweight
32 | Snap_refreshfare
22 | Snap_mobilenumber
33 | Snap_hardwareconfiguration
34 | resetpassword button
37 | userole_errormessage
36 | fareconfiguration_effectivedate
35 | Snapshot_logout
38 | Snapshot_urlrefresh