## Bug Report
| Project: | Nagpur-Mumbai | Assign To
| Module Name: | Toll 360 | Tested By
| Operating System: | Window 10
Version:
Defect Id | Description | Test case Id | Bug Type | Reproducible Steps | Status | Severity | Priority | Test Cycle | Snapshot | Fixed by | Developer comment | QC Comment | Dated | Assignee Name | Comment
1 | Clicking on dashboard shows that "Dashboard Works!". |  | Suggestion | Click on dashboard. | Not Reproduced | Trivial | Low | Test Cycle 2 |  |  | Done |  | 2021-04-22
2 | Unable to create client from client configuration. Save button or icon not reflecting. |  | Validation | Click on client configuration. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-04-22
3 | Unable to create plaza as client can't be created. |  | Validation | Click on plaza configuration. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-04-22
4 | What is the use of FTP path, login id, password, data send/receive API? |  | Suggestion | Creation of plaza in plaza configuration. | Open | Trivial | Low | Test Cycle1 |  | Done | FTP will remove from UI and API path help to transfering the data | Done | 2021-04-22
5 | Client id in client configuration grid is not in numeric series. |  | GUI | Click on client configuration. | Fixed | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid | Done | 2021-04-22
6 | Plaza id in plaza configuration grid is not in numeric series. |  | GUI | Click on plaza configuration. | Fixed | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid | Done | 2021-04-22
7 | Lane id in lane configuration grid is not in numeries series. |  | GUI | Click on lane configuration. | Fixed | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid | Done | 2021-04-22
8 | In hardware configuration, while creating new hardware, dropdown filter of plaza is reflecting only one plaza name for selection. |  | Validation | Click on hadrware configuration -> Click on + button. | Fixed | Major | High | Test Cycle1 |  |  | Plaza will display according to client | Done | 2021-04-22
9 | In hardware configuration, first row in a grid is not reflecting completely. |  | GUI | Click on hardware configuration. | Fixed | Medium | Medium | Test Cycle1 |  |  | user Screen resolution 1368*768 | Done | 2021-04-22
10 | Hardware ID in hardware configuration grid is not in numeric series. |  | GUI | Click on hardware configuration. | Fixed | Medium | Medium | Test Cycle1 |  |  | Last created and modified data come first poition of grid | Done | 2021-04-22
11 | The names for Vehicle Class is not matching. While adding a new vehicle, vehicle class mapping screen was shown. |  | GUI | Click on vehicle class -> Click on + button. | Fixed | Trivial | Low | Test Cycle1 |  |  | Working fine | Done | 2021-04-22
12 | In vehicle class configuration, first row in a grid is not reflecting completely names of column. |  | GUI | Click on vehicle class. | Fixed | Medium | Medium | Test Cycle1 |  |  | user Screen resolution 1368*768 | Done | 2021-04-22
13 | Unable to create a vehicle class. AVC class and IHMCL class not configured. |  | Validation | Click on vehicle class -> Click on + button. | Fixed | Major | High | Test Cycle1 |  |  | Import the ACV class | Done | 2021-04-22
14 | Fare mapping is not opening since there was not vehicle class configured. |  | Functional | Click on fare mapping. | Open | Major | High | Test Cycle1 |  |  | Done | Done | 2021-04-22
15 | Role id in role configuration is not in numeric series. |  | GUI | Click on role configuration. | Fixed | Trivial | Low | Test Cycle1 |  |  | Last created and modified data come first poition of grid | Done | 2021-04-22
16 | In user configuration, only one plaza was shown in dropdown filter. |  | Validation | Click on user configuration. | Fixed | Major | High | Test Cycle1 |  |  | Plaza will display according to client | Done | 2021-04-22
17 | Clicking on reports, error 404 is reflecting. |  | Functional | Click on reports. | Not Reproduced | Major | High | Test Cycle1 |  |  | Reporting is pending |  | 2021-04-22
18 | In fare mapping, the effective date calander is not defined correctly. No year could be mentioned and even date can't be selected. |  | Functional | Click on fare mapping. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | Continuation
19 | Toll fare, return fare, penalty fare and overweight fare can't be configured from application. |  | Functional | Click on fare mapping. | Fixed | Major | High | Test Cycle1 |  |  | all journey and class auto populate according to plaza and class details. just need to click on Toll Fare/Return fare/Penalty Fare/OverWeight Fare | Done | Continuation
20 | Entry in fare mapping grid can't be edited. |  | Functional | Click on fare mapping. | Fixed | Major | High | Test Cycle1 |  |  | just need to click on Toll Fare/Return fare/Penalty Fare/OverWeight Fare | Done | Continuation
21 | New entry can't be created, message reflecting as "Effective date must be greater than current date". |  | Functional | Click on fare mapping. | Fixed | Major | High | Test Cycle1 |  |  | Toll Rate must be set for future not for current and back date | Done | Continuation
22 | In user configuration, entries in a grid can't be edited. |  | Functional | Click on user configuration. | Fixed | Major | High | Test Cycle1 |  |  | all edit icon are at right of grid, please use horizontal scroll to edit | Done | Continuation
23 | Plaza configuration entries can't be edited. |  | Functional | Click on plaza configuration. | Fixed | Major | High | Test Cycle1 |  |  | all edit icon are at right of grid, please use horizontal scroll to edit | Done | Continuation
24 | Lane configuration entries can't be edited. |  | Functional | Click on lane configuration. | Fixed | Major | High | Test Cycle1 |  |  | all edit icon are at right of grid, please use horizontal scroll to edit | Done | Continuation
25 | Hardware configuration entries can't be edited. |  | Functional | Click on hardware configuration. | Fixed | Major | High | Test Cycle1 |  |  | all edit icon are at right of grid, please use horizontal scroll to edit | Done | Continuation
26 | Vehicle class entries can't be edited. |  | Functional | Click on vehicle class. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | Continuation
27 | Unable to save toll fare, return fare, penlty fare and overweight fare. |  | Functional | Enter numeric value in the text box and press enter key. | New | Major | High | Test Cycle1 |  |  | Not a bug: toll always save after clicked on save button | Done | Continuation
28 | Unable to visualize create new entry pop-up, message reflecting as "Success". |  | Functional | Click on create new entry in fare mapping. | New | Major | High | Test Cycle1 |  |  | Not a bug | Done | Continuation
29 | Spell check - Slot Id is mentioned as Sloat Id. |  | Typo | See for the column 2. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-05
30 | While creating a new entry, in shift dropdown filter, rather than timmings , shift 1, shift 2 and shift 3 needs to be displayed. |  | Validation | Click on create new entry. | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-05
31 | Click on Print button, the printing of receipt required receipt number. On GUI no receipt number is displayed. |  | Functional | Click on Print button. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-05
32 | Shift end declaration is missing in the module. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-05
33 | Receipt number is only mentioned in the generated receipt, but also required to be displayed in the grid. |  | GUI |  | Fixed | Medium | High | Test Cycle1 |  |  | Allotment Receipt Number displayed | Done | 2021-05-05
34 | Shift timming is required to be renamed as Shift Id in the column. |  | GUI |  | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-05
35 | Mid shift declare could be declared for future date. The mid shift should be allowed only for current running shift only. |  | Functional | Click on mid shift and declare amount for future date. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-05
36 | Reset button is not available to clear entries from a grid. |  | Functional | See for the review transaction page. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-07
37 | Filter data details are not hiding from the form. |  | Validation | Check for the spelling of Proof in transaction details pop-up. | Fixed | Major | High | Test Cycle1 |  |  | Done:its will show/hide on click of filter icon | Done | 2021-05-07
38 | Spell check: Proof spelling is displaying as Proff in transaction details. |  | Typo | Click on filter data button. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-07
39 | Only last transaction details is displaying in the transaction when filtered. Unable to switch to another transaction in the same pop-up untill reviewed. |  | Functional | See for the transaction details pop-up. | Fixed | Major | High | Test Cycle1 |  |  | Need discussion | Done | 2021-05-07
40 | The image and video displaying are same for every transaction. Even video is not buffering. |  | Functional | See for the transaction details pop-up. | Fixed | Major | High | Test Cycle1 |  |  | its dummy data | Done | 2021-05-07
41 | Separate pop-up is required for the filter data, which will be very much clear in visual and functional process. |  | Validation | Click on filter data button. | Fixed | Medium | Medium | Test Cycle1 |  |  | Need discussion | Done | 2021-05-07
42 | The page for review required filter is not refreshing. The transaction is displayed in the grid after review. |  | Functional | Select review required filter from filter data. | Fixed | Major | High | Test Cycle1 |  |  | Need discussion | Done | 2021-05-07
43 | While clicking on the clearance button, mid clearance is only possible. Even allotment amount doesn't changes as per entered denominations. |  | Functional | Click on clearance button, enter denominations and click on save button. | Fixed | Major | High | Test Cycle1 |  |  | Allotment amount is that fixed its will never change.each clearence willstore in sperate coloum that is deposit. Final stalement will done in shift close. | Done | 2021-05-07
44 | For current date and shift, mid shift declare is not allowed. Message displayed as "Mid shift declare is not allowed for future shift." |  | Functional | Declare mid shift. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-07
45 | After clearance of a particular user and shift, the shift status is showing as pending in the grid. |  | Functional | See for the details in a grid after clearance. | Fixed | Major | High | Test Cycle1 |  |  | Shift showing pending untill its is not closed and when its closed it will remove from the grid | Done | 2021-05-07
46 | While closing a sift, message appear as "Lane is not close this shift". The statement is contradictory. |  | Functional | Close a shift from shift details. | Fixed | Major | High | Test Cycle1 |  |  | this meaasge is used to validate the lane trans are synced or not | Done | 2021-05-08
47 | Click on review transaction, and the details of last processed transaction automatically displayed without selecting filter data. |  | Functional | Click on review transaction. | Fixed | Major | High | Test Cycle1 |  |  | Need discussion | Done | 2021-05-08
48 | Lane transaction details-1 or 2 or 3 is displayed in a pop-up, which is not required. Clicking on a transaction should display details of that particular transaction. |  | Suggestion | Click on transaction displaying in a grid. | Fixed | Major | High | Test Cycle 2 |  |  | We put the Lane Transaction details-Transaction Number(1) | Done | 2021-05-08
49 | Naming convention issue (Violation) in Transaction Type Details page.(central Server) |  | GUI | Naming convention issue | Fixed | Trivial | Low | Test Cycle1 |  |  | Done | Done | 2021-05-08
50 | In Client configuration page mobile number should be 10 digit only. (central Server) |  | GUI | Mobile number issue | Fixed | Medium | Medium | Test Cycle1 |  |  | In our country mobile number length is increased up to 11 digit (Not a bug) | Done | 2021-05-08
51 | User is not able to click on status check box field popup message should be proper displayed and close.(Client configuration page) |  | GUI | Message issue | Fixed | Major | High | Test Cycle1 |  |  | Share Snapshot | Done | 2021-05-08
52 | Special character should not be allowed in Name, Address, Mobile Number, Email (except@) (Client configuration page). |  | GUI | Special charcter issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Done:We can ignore in name and mobile number | Done | 2021-05-08
53 | In Exempt configuration page filter search functionality are not working. |  | Functional | Search Issue | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-08
54 | Creating or Editing fields Special character should not be allowed in Exemption Name Field. |  | GUI | Special charcter issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-08
55 | Creating or Editing fields Special character should not be allowed in Plaza Configuration Page. |  | GUI | Special charcter issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-08
56 | Page should be maximized or minimized over clicking mouse. The zoom-in and zoom-out option should be there with a single button. |  | GUI | Max or min by click mouse | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-08
57 | active or Inactive record should be update in plaza mapping page. |  | Functional | Active/Inactive | New | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-08
58 | Creating or Editing records Special character should not be allowed in Lane Configuration Page (Lane IP). |  | GUI | Special charcter issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Working Fine, need to press tab or click the save icon to check the validaton (Not a bug) | Done | 2021-05-08
59 | Creating or Editing records Special character should not be allowed in Vehicle class Configuration Page (Vehicle Weight). |  | GUI | Special charcter issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Working Fine (Not a bug) | Done | 2021-05-08
60 | In fare configuration Page Refresh button is not working.(Before user search the records). |  | Functional | Refresh button issue | Fixed | Major | High | Test Cycle 2 |  |  | Reload button is depend on effective date selection, for example select any date and need to click on reload button its will display data depend selected date. today is 9th of may and you choose 10th may and clieck on reload then it will show data for 9th may and date will be auto set for 9th may. This is need to be done manually | Done | 2021-05-08
61 | Column name 'Connection Address' should be proper visible in hardware configuration page. |  | GUI | visibility issue | Fixed | Medium | Medium | Test Cycle1 |  |  | already shared: used Screen resolution 1368*768 | Done | 2021-05-10
62 | Reset Password save button should be required. |  | Functional | Button | Fixed | Major | High | Test Cycle1 |  |  | Done : Reset password not used for super account, You can create new user and test again | Done | 2021-05-10
63 | Logout popup window cross sign should be removed. |  | GUI | Cross icon | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-10
64 | User click on save button effective date should not be refreshed,data should be saved only. (Fare Configuration) |  | Functional | Save button | Fixed | Major | High | Test Cycle1 |  |  | Its already described | Done | 2021-05-10
65 | Error message should be proper displayed, the case of before user enter the same role name after clicking on save button. (User role page). |  | GUI | Message issue | Fixed | Medium | Medium | Test Cycle 2 |  |  | Working Fine | Done | 2021-05-10
66 | User is able to logged in the webpage at a time user clicking on url refresh button, all page should be closed and session logout automatically.(show only login page) |  | Functional | page issue | Fixed | Major | High | Test Cycle 2 |  |  | Done | Done | 2021-05-10
67 | User entering the same records in hardware configuration page, same records should not be saved in multiple times. |  | Functional | Duplicate records | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-11
68 | Footer of the page Naming name should be 'Superwave Toll 360', and link should not be highlighted in new page. |  | GUI | Naming convention issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-11
69 | Only Single space should be possible, not in multiple space saved, in plaza configuration (Plaza Name). |  | GUI | Space issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-11
70 | Only Single space should be possible, not in multiple space saved, in role and right configuration page. |  | GUI | Space issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-11
71 | Record window should be closed, before user saved the records. |  | GUI | Demo Popup Window | Fixed | Medium | Medium | Test Cycle1 |  |  | Not a bug this is demo app will remove after lane module ready | Done | 2021-05-12
72 | User search the record date of 8th may but message is coming "No data Found". |  | GUI | No data Found msg | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-12
73 | All column name fields should be proper displayed, and date filter search records should be proper place. |  | GUI | Filter search | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-12
74 | User is able to clicking on cross sign icon only filtered records should be reseted. Click on cross icon grid number of rows increases. |  | GUI | Filter search | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-12
75 | Before Review records saved successfully but popup window still there, wondow should be removed. |  | Functional | Review page window | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-12
76 | User is able to click on Save button message is showing "Mid clearance not allowed for future shift." (Cashup) |  | GUI | Msg Issue | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-12
77 | User alloted the cash receipt in future date easily. (Cashup) |  | Functional | Future date issue | Fixed | Medium | Medium | Test Cycle1 |  |  | cash allotment can be done for future. Because its need berofe shift start | Done | 2021-05-12
78 | Records already displayed in grid fields, user give the print message is showing 'No Data Found'. |  | GUI | Msg Issue | Fixed | Medium | Medium | Test Cycle1 |  |  | SELECT on allotment option | Done | 2021-05-12
79 | In Review transaction page, search records page header name will be "Lane Transactions Details" Only. |  | GUI | Page header name | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-12
80 | User is able to select central server and create the user, user is not showing plaza server details. |  | Functional | data issue | Fixed | Major | High | Test Cycle1 |  |  | create central server user no need to sink to plaza | Done | 2021-05-17
81 | Naming convention issue in create user form (central server) |  | GUI | naming | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-17
82 | On shift close in Cashup, AmountAllocation should reflect total amount. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-18
83 | There should an option to scrap receipt in Review Transaction module. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-18
84 | Form page is not showing before User given the rights in cashiour user. |  | Functional | User rights issue | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-18
89 | Company Name "SCAIPL" should be proper displayed.(center and plazas) |  | GUI |  | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-19
90 | Copyrights and scroll bar should be proper displayed. |  | GUI |  | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-19
91 | User is able to update the fare in center server, effective date and amount should be reflected, the reasion for softomation service automatically stuck. |  | Functional | Service issue | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-19
92 | User is not logged in plaza level, before user assign the rights in admin user, after that see the user details not found in plaza level(192.168.1.36) or unauthorized user issue generated. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Not a bug: OnlyPlaza user access the plaza application | Done | 2021-05-20
93 | User open the page message is showing 'No data found'. |  | GUI |  | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-20
94 | User is able to close the shift message is showing exit lane data is pending, but user see the review transaction page no data found. |  | Functional | Close shift issue | Fixed | Major | High | Test Cycle1 |  |  | Check again | Done | 2021-05-20
95 | User is able to see 2 times same shift generated, shifts should be one time generated. |  | Functional | Multiple times shift generated | Fixed | Major | High | Test Cycle1 |  |  | Not a bug: its becase cash alloted for multiple user | Done | 2021-05-20
96 | User already audit the transactions after going to close the shift message is showing audit is pending for this shift. |  | Functional | shift close issue | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-21
97 | Client option should not be hide, without select client can't be displayed in grid fields. |  | GUI |  | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-21
98 | Operator wise report not generated, message is showing 'something went wrong.' |  | GUI |  | Fixed | Medium | Medium | Test Cycle1 |  |  | Done | Done | 2021-05-22 | Madhav Singh
99 | Traffic Revenue with ETC report not generating. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-22 | Madhav Singh
100 | Cash allotment, declared amount, shortage, transaction amount are not showing in cashup report. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-22 | Madhav Singh
101 | Denomination amount should be reflected in alloted amount in cashup clearence page. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-22 | Madhav Singh
102 | Visibility should be proper displayed (year, AM,PM),all dropdown field should 'ALL'option required check or uncheck. |  | GUI | Suggestion | Open | Medium | Medium | Test Cycle1 |  |  | Done | Reopen (All Option Should be pending) | 2021-05-22 | Madhav Singh
103 | On shift close in Cashup, Amount Allocation should reflect total amount. |  | Functional | In review transaction, check for amount allocation amount. | Fixed | Major | High | Test Cycle 2 |  |  | Done | Done | 2021-05-22 | Pankaj sharma
104 | There should an option to scrap receipt in Review Transaction module. |  | Functional | Click on review transaction, check for scrap receipt. | Fixed | Major | High | Test Cycle 2 |  |  | Done | Done | 2021-05-22 | Pankaj sharma
105 | After creating any client, a client shouldn't have authorized to activate and deactivate users/plaza. |  | Functional | Create a new client and check for credentials. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-22 | Pankaj sharma
106 | The client should be restricted for being login when disabled. |  | Functional | Login with client with invalid credentials/disabled. | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-22 | Pankaj sharma | This bug duplicate if you have already shared bugs id 105
107 | In cashup Clearence before user see the records in grid section after closed the shift in Admin User, all records automatically removed (without clearence in TC001 User). |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  | Done | Done | 2021-05-23 | Madhav Singh
108 | All Unreview transactions should be displayed in grid section. User not reviewed the transactions and going to cashup page and close the shift, message is showing audit is pending, but after that looking the review page data not found-(User is not able to want search option). |  | Functional |  | Open | Major | High | Test Cycle1 |  |  | Done | If the records existing will be showing on the grid / Other wise No Records found/ whenever user search the records filtered option./Not Fixed | 2021-05-23 | Madhav Singh
109 | web page already open user going to logout the application message is showing something went wrong. |  | Functional |  | Open | Major | High | Test Cycle1 |  |  | Need Steps to generate | Some times issue has been generated. | 2021-05-24 | Madhav Singh
110 | Only Single user receipt should be generated in Cash allotment receipt. |  | Functional |  | Open | Major | High | Test Cycle1 |  |  | Done |  | 2021-05-24 | Madhav Singh
111 | Traffic revenue with ETC report amount should be reflected. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Working Fine | Now generated and Fixed | 2021-05-24 | Madhav Singh
112 | Consolidated report amount should be reflected. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Working Fine | Now generated and Fixed | 2021-05-24 | Madhav Singh
113 | Cancelled transaction report amount should be reflected. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Not a bug (Entry Lane data not found) | Now generated and Fixed | 2021-05-24 | Madhav Singh
114 | transaction report data is not showing before user generated the report. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Not a bug (Entry Lane data not found) | Now generated and Fixed | 2021-05-24 | Madhav Singh
115 | Category required to be displayed on screen as a dropdown filter. |  |  |  | Fixed | Major | High | Test Cycle1 |  |  |  |  | 2021-05-24 | Pankaj sharma
116 | Sub-category must be defined as per selected filter. |  | Functional |  | Fixed | Major | High | Test Cycle1 |  |  |  |  | 2021-05-24 | Pankaj sharma
117 | In the shift tab, all sfifts are not required, as per selection of date and time the shift could be visible on screen. |  | Validation |  | New | Major | High | Test Cycle1 |  |  | Need Discussion | Done | 2021-05-24 | Pankaj sharma
118 | There are various vehicle classes displaying on screen, selectable class filter/dropdown must be there. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Done | As a suggestion | 2021-05-24 | Pankaj sharma
119 | Lane selection must be a dropdown filter. |  | Validation |  | New | Major | High | Test Cycle1 |  |  | Done | As a suggestion | 2021-05-24 | Pankaj sharma
120 | Operator are not been required with a checkbox. Need a dropdown filter. |  | Validation |  | New | Major | High | Test Cycle1 |  |  | Done | As a suggestion | 2021-05-24 | Pankaj sharma
121 | It's difficult to recognize the type of transaction selected through checkbox. Need a dropdown filter. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Done | As a suggestion | 2021-05-24 | Pankaj sharma
122 | Payment type are all selected through checkbox, Selectable dropdown is needed. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Done | As a suggestion | 2021-05-24 | Pankaj sharma
123 | User search the records exemption transaction not found before user created the transaction. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Done | As discussed search option required for vehicle based. | 2021-05-25 | Madhav Singh
124 | In Report category type transactional and sub category Exempt vehicle class report should be generated. |  | Functional |  | New | Major | High | Test Cycle1 |  |  | Done | the reason for data not showing in review txn | 2021-05-25 | Madhav Singh
125 | In Review transaction details page - Only show Lane Transaction Details, should not be displayed transaction Number (10) |  | GUI |  | Open | Major | High | Test Cycle1 |  |  | Done | Not done please removed transaction number(10) | 2021-05-25 | Madhav Singh
126 | Only Single reciept details should be displayed before user print the cash allotment. |  | GUI |  | New | Medium | Medium | Test Cycle1 |  |  | Done | Fixed | 2021-05-26 | Madhav Singh
Cosmetic
Test Cycle1
High | Blocker | New |  | Functional | Test Cycle 2
Medium | Major | Open |  | Validation | Test Cycle 3
Low | Medium | Fixed |  | Truncation | Test Cycle 4
| Trivial | Reopen |  | Cosmetic | Test Cycle 5
|  | Verified |  | GUI | Test Cycle 6
|  | Closed |  | Typo | Test Cycle 7
|  | Differed |  | Suggestion | Test Cycle 8
|  | Not Reproduced |  | Requirement | Test Cycle 9
|  | New(Re QA) |  |  | Test Cycle 10
Pankaj Sharma

## Developer
Bug No 111 | Bug No 112

## Evidence
Defect ID
Defect Id | Snapshot |  | 123
113
114
125
115
112
89
126
90
91
92
93
94
95
96
97
98
100
101
102
107
108
109