## R&D
Project Name |  |  | Project Duration (Days) |  | Project Start Date | Project End Date | Progress
[7 empty] | Days Passed | Project Complete %
Toll 360 Solution Data Management |  |  | Planned | 235 | 2021-03-22 | 2021-05-21 |  | 79.17%
|  |  | Actual | 235 | 2021-03-25 | 2021-05-21
Task ID | Task Description | Sub Task | Duration (Calender Man Days) |  | Start Date | End Date | Task Status |  | Remark
1 | Data Base | Design | Planned | 6 | 2021-03-22 | 2021-03-28 | Closed
|  |  | Actual | 6 | 2021-03-25 | 2021-03-31
|  | Development | Planned | 30 | 2021-03-29 | 2021-04-28 | In Progress
|  |  | Actual | 30 | 2021-03-29 | 2021-04-28
2 | Control Room (Back Office Application) | Template Design | Planned | 3 | 2021-04-01 | 2021-04-04 | Closed
|  |  | Actual | 3 | 2021-04-01 | 2021-04-04
|  | User Management | Planned | 2 | 2021-04-04 | 2021-04-06 | Closed
|  |  | Actual | 2 | 2021-04-04 | 2021-04-06
|  | Role and Rights | Planned | 20 | 2021-04-05 | 2021-04-25 | Closed
|  |  | Actual | 20 | 2021-04-05 | 2021-04-25
|  | Plaza Configuration | Planned | 2 | 2021-04-06 | 2021-04-08 | Closed
|  |  | Actual | 2 | 2021-04-06 | 2021-04-08
|  | Plaza Mapping | Planned | 4 | 2021-04-10 | 2021-04-14 | Closed
|  |  | Actual | 4 | 2021-04-10 | 2021-04-14
|  | Fare Mapping | Planned | 4 | 2021-04-12 | 2021-04-16 | Closed
|  |  | Actual | 4 | 2021-04-12 | 2021-04-16
|  | Lane Configuration | Planned | 3 | 2021-04-14 | 2021-04-17 | Closed
|  |  | Actual | 3 | 2021-04-14 | 2021-04-17
|  | Reporting | Planned | 20 | 2021-05-01 | 2021-05-21 | In Progress
|  |  | Actual | 20 | 2021-05-01 | 2021-05-21
|  | Testing | Planned | 40 | 2021-04-10 | 2021-05-20 | In Progress
|  |  | Actual | 40 | 2021-04-10 | 2021-05-20
3 | Plaza Server (Back Office Application) | Template Design | Planned | 3 | 2021-04-03 | 2021-04-06 | Closed
|  |  | Actual | 3 | 2021-04-03 | 2021-04-06
|  | User Management | Planned | 2 | 2021-04-06 | 2021-04-08 | Closed
|  |  | Actual | 2 | 2021-04-06 | 2021-04-08
|  | Role and Rights | Planned | 20 | 2021-04-08 | 2021-04-28 | Closed
|  |  | Actual | 20 | 2021-04-08 | 2021-04-28
|  | Lane Configuration | Planned | 4 | 2021-04-16 | 2021-04-20 | Closed
|  |  | Actual | 4 | 2021-04-16 | 2021-04-20
|  | Audit | Planned | 5 | 2021-05-01 | 2021-05-06 | Closed
|  |  | Actual | 5 | 2021-05-01 | 2021-05-06
|  | LSDU | Planned | 10 | 2021-04-20 | 2021-04-30 | Open |  | Depnd on Lane application
|  |  | Actual | 10 | 2021-04-20 | 2021-04-30
|  | Reporting | Planned | 20 | 2021-05-01 | 2021-05-21 | In Progress
|  |  | Actual | 20 | 2021-05-01 | 2021-05-21
|  | Cash UP | Planned | 10 | 2021-05-01 | 2021-05-11 | Closed
|  |  | Actual | 10 | 2021-05-01 | 2021-05-11
|  | Testing | Planned | 40 | 2021-04-10 | 2021-05-20 | In Progress
|  |  | Actual | 40 | 2021-04-10 | 2021-05-20
4 | Control Room (Data Transfer Application) | API for Data Synchronization | Planned | 4 | 2021-04-20 | 2021-04-24 | Closed
|  |  | Actual | 4 | 2021-04-20 | 2021-04-24
|  | API for Image/Video Synchronization | Planned | 4 | 2021-04-23 | 2021-04-27 | Closed
|  |  | Actual | 4 | 2021-04-23 | 2021-04-27
|  | Testing | Planned | 10 | 2021-04-25 | 2021-05-05 | In Progress
|  |  | Actual | 10 | 2021-04-25 | 2021-05-05
5 | Plaza Server (Data Transfer Application) | API for Data Synchronization | Planned | 4 | 2021-04-25 | 2021-04-29 | Closed
|  |  | Actual | 4 | 2021-04-25 | 2021-04-29
|  | API for Image/Video Synchronization | Planned | 4 | 2021-04-27 | 2021-05-01 | Closed
|  |  | Actual | 4 | 2021-04-27 | 2021-05-01
|  | Testing | Planned | 10 | 2021-04-30 | 2021-05-10 | Closed
|  |  | Actual | 10 | 2021-04-30 | 2021-05-10
6 | Lane Integration | API for Data Synchronization | Planned | 4 | 2021-04-25 | 2021-04-29 | Closed |  | Pending from superwave
|  |  | Actual | 5 | 2021-05-01 | 2021-05-06
|  | API for Image/Video Synchronization | Planned | 4 | 2021-04-27 | 2021-05-01 | Closed |  | Pending from superwave
|  |  | Actual | 5 | 2021-05-01 | 2021-05-06
|  | Testing | Planned | 15 | 2021-05-01 | 2021-05-16 | Open |  | Pending from superwave
|  |  | Actual | 15 | 2021-05-06 | 2021-05-21
Formulas:
Project End Date = [Project Start Date]+F8